## 17-239
Task Name | Estimate time( hour) | Take by | Actual Time | Status | Date Doing | Complete Process | Note
Requirement analyze | 16 | Nguyen Van A |  | Done |  | 0
[Report 1] Project Information | 2 | Nguyen Van A |  | Done |  | 2
[Report 1] Introduction | 2 | Nguyen Van A |  | Done |  | 2
[Report 1] Current Situation | 2 | Nguyen Van A |  | Done |  | 2
[Report 1] Problem Definition | 2 | Nguyen Van A |  | Done |  | 2
Draw ERD diagram | 8 | Nguyen Van A |  | Done |  | 8
Deploy database to AWS (empty database) | 4 | Nguyen Van A |  | Done |  | 4
Learning ReactJS | 10 | Nguyen Van A |  | Done |  | 10
Total | 46 |  | 93.88% |  | Done task: | 65.22%
Requirement analyze | 12 | Nguyễn Van B |  | Done |  | 12
[Report 1] Proposed Solution | 2 | Nguyễn Van B |  | Done |  | 2
[Report 1] Functional Requirement | 5 | Nguyễn Van B |  | Done |  | 5
[Report 1] Roles and Responsibility | 2 | Nguyễn Van B |  | Done |  | 2
Learning Spring for Restful API | 10 | Nguyễn Van B |  | Done |  | 10
Learning Spring Security | 10 | Nguyễn Van B |  | Done |  | 10
Draw Usecase Diagram | 14 | Nguyễn Van B |  | Done |  | 14
Total | 55 |  | 112.2% |  | Done task: | 100%
[UI Mockup Web] Login/Register Screen | 3 | Nguyễn Van C |  | Done |  | 3
[UI Mockup Web] Home (Item Listing) Screen | 4 | Nguyễn Van C |  | Done |  | 4
[UI Mockup Web] Auction posting screen | 3 | Nguyễn Van C |  | Done |  | 3
[UI Mockup Web] Item Screen | 4 | Nguyễn Van C |  | Done |  | 4
[UI Mockup Web] Cart Screen | 5 | Nguyễn Van C |  | Done |  | 5
[UI Mockup Web] Checkout Screen | 5 | Nguyễn Van C |  | Done |  | 5
[UI Mockup Web] Personal Item Screen | 5 | Nguyễn Van C |  | Done |  | 5
[UI Mockup Web] Notification screen | 5 | Nguyễn Van C |  | Done |  | 5
[UI Mockup Web] Admin's auction management screen | 5 | Nguyễn Van C |  | Done |  | 5
[UI Mockup Web] Admin's user management screen | 5 | Nguyễn Van C |  | Fail |  | 5
[UI Mockup Web] Admin's category management screen | 5 | Nguyễn Van C |  | Done |  | 5
[UI Mockup Web] Admin's Report screen | 4 | Nguyễn Van C |  | Done |  | 4
Requirement analyze | 8 | Nguyễn Van C |  | Done |  | 8
Total | 61 |  | 124.5% |  | Done task: | 86.89%
Requirement analyze | 9 | Nguyên Van D |  |  |  | 9
[UI Mockup Mobile] Login/Register Screen | 2 | Nguyên Van D |  | Pending |  | 0
[UI Mockup Mobile] Home (Item Listing) Screen | 3 | Nguyên Van D |  | Done |  | 3
[UI Mockup Mobile] Auction posting screen | 3 | Nguyên Van D |  | Done |  | 3
[UI Mockup Mobile] Item Screen | 3 | Nguyên Van D |  | Done |  | 3
[UI Mockup Mobile] Cart Screen | 4 | Nguyên Van D |  | Done |  | 4
[UI Mockup Mobile] Checkout Screen | 2 | Nguyên Van D |  | Done |  | 2
[UI Mockup Mobile] Personal Item Screen | 3 | Nguyên Van D |  | Done |  | 3
[UI Mockup Mobile] Notification screen | 2 | Nguyên Van D |  | Done |  | 2
[UI Mockup Mobile] Admin's auction management screen | 5 | Nguyên Van D |  | Done |  | 5
[UI Mockup Mobile] Admin's user management screen | 5 | Nguyên Van D |  | Done |  | 5
[UI Mockup Mobile] Admin's category management screen | 2 | Nguyên Van D |  | Done |  | 2
[UI Mockup Mobile] Admin's Report screen | 3 | Nguyên Van D |  | Done |  | 3
[Implement UI] Login/Register Screen | 2 | Nguyên Van D |  | Done |  | 2
[Implement UI] Home (Item Listing) Screen | 4 | Nguyên Van D |  | Done |  | 4
[Implement UI] Cart Screen | 4 | Nguyên Van D |  | Done |  | 4
[Android] Research Verify | 5 | Nguyên Van D |  | Done |  | 5
Total | 52 |  | 106.1% |  | Done task: | 96.15%